## Sheet1
ASCE NORTH JERSEY BRANCH EVENT CHECKLIST
NAME OF EVENT | XXXXX | DATE OF EVENT: | 2013-05-08
TECHNICAL GROUP
Item | Timeline Prior to Event | Notes | Person Responsible | Task Due Date | Task Completed
Identify and Contact Speaker | 6 weeks |  | Chair | 2013-03-27 | Done
Establish Venue | 6 weeks |  | Board VP | 2013-03-27 | Done
Create Tech Group Event Report | 6 weeks | Use file provided | Chair | 2013-03-27 | Done
Create Flyer/Advertise | 5 weeks | Include directions/parking instructions / Make checks payable to ASCE North Jersey Branch | Chair | 2013-04-03 | Done
Update Website | 5 weeks | See usernames and passwords below. Contact Steve Alpert (salpert@HNTB.com) with any questions on the website | Chair | 2013-04-03 | Done
Finalize Venue | 5 weeks |  | Board VP | 2013-04-03 | Done
Transportation/Hotel for Speaker(s) | 4 weeks |  | Chair | 2013-04-10 | Done
Handouts | 4 weeks |  | Chair | 2013-04-10 | Done
PDH Accreditation | 3 weeks | Chair is to submit the following items at least three weeks prior to the seminar date to Satish Patel through email, Satish.Patel@jacobs.com: 1. Electronic file of presentation (pdf file is sufficient) 2. Bio/Resume(s) of the speaker(s) 3. Detailed timed outline of presentation showing breakdown of items being presented. 4. 10 Questions speaker would ask to assess learning. | Chair | 2013-04-17 | Done
Plaque(s) | 2 weeks | Contact Greg Landry | Board Pres-Elect | 2013-04-24 | Done
Request Checks from Treasurer | 2 weeks | Do not request checks last minute, you may not get them | Chair | 2013-04-24 | Done
Create Alphabetized List of Attendees by Company then Last Name | 1 week |  | Board Pres-Elect | 2013-05-01 | Done
PDH Sign-in Sheet/Certificate | 1 week |  | Chair | 2013-05-01 | Done
Name Tags | 1 week |  | Chair | 2013-05-01 | N/A
Get Screen/Podium | 1 week |  | Chair | 2013-05-01 | N/A
Get Projector/Laptop/Extension cord | 1 week |  | Chair | 2013-05-01 | N/A
Receipts | 1 week |  | Board VP | 2013-05-01 | Done
Registration Desk (2 volunteers) | 1 week |  | Chair | 2013-05-01 | Done
Photographer | 1 week |  | Board VP | 2013-05-01 | Done
Check to Venue | Same Day |  | Board Treasurer | 2013-05-08 | Done
Receive Checks at Door | Same Day | Make sure checks are endorsed properly. Cash is discouraged. | Chair | 2013-05-08 | Done
Checks/Cash to Treasurer | Day after | Tech Lead to keep Cash and write check for amount. | Chair | 2013-05-09
Expense Form to Treasurer | Day after | Use file provided. Submit electronically to Treasurer | Chair | 2013-05-09
Tech Group Event Report to Treasurer | Day after | Submit electronically to Treasurer | Chair | 2013-05-09 | Done
Receipts to Treasurer | Day after | Submit electronically to Treasurer | Chair | 2013-05-09
Event Chair to write article for newsletter incl. photos | Week after | Submit electronically to President-Elect | Chair | 2013-05-15